## Physical final 4th cycle
Department of Social Welfare and Development (DSWD)
ACCOMPLISHMENT REPORT
RE: Supplementary Feeding Program (4th Cycle)
As of October 31, 2014
REGION | Physical Accomplishment | [11 empty] | Fund Obligations | [29 empty] | Remarks
| Target per WFP |  |  | Adjusted Target |  |  | Total Served | [5 empty] | Amount Allocated to LGUs (Grants) | Fund Obligated | Funds Spent for the Rice and Utensils c/o FO | % | Rate of Accomplishment | Rank | MOA with LGUs | Fund Transfer | Procurement of Utensils |  |  |  | Ranking |  | Nutritional Status | [12 empty] | % of Increase for Normal Status | % of Decrease for Underweight | % of Decrease for Overweight
| LGUs | DCCs | Children | LGUs | DCCs | Children | LGUs | DCCs | Children |  |  | % | [14 empty] | Number of Children Weighed | Nutritional Status before the start of Feeding | [5 empty] | Nutritional Status at the latest
[10 empty] | Cost* | [17 empty] | # DCCh with/Normal Status | % | # Underweight Ch | % | # Overweight | % | # DCCh with/Normal Status | % | # Underweight Ch | % | # Overweight | %
I | 125 | 3282 | 97026 | - | 3298 | 97253 | 0 | 2184 | 64813 | 9479850 | 0 | 66.7996 | 162640800 | 151012680 | #REF! | 92.8504 | 92.8504 | 4 | 125 | 125 | 125 | procurement of food commodities still on process in some LGUs; upland communities road not yet accessible for the delivery of food commodities | 1 | 1 | 3 | 1 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
II | 93 | 2671 | 74130 | 0 | 0 | 0 | 0 | 2046 | 61157 | 25254400 | 0 | 82.4997 | 120945800 | 122066471 | #REF! | 100.9266 | 100.9266 | 1 | 93 | 93 | 87 | partial delivery of utensils done | 2 | 2 | 4 | 2 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
III | 130 | 3947 | 147000 | - | 0 | 0 | 0 | 3740 | 136386 |  | 0 | 92.7796 | 350649000 | 199425932 | #REF! | 56.8734 | 56.8734 | 1 | 128 | 128 |  | 2 LGUs to start this week while 3 LGUs with previous unliquidated funds (past projects) | 3 | 3 | 6 | 3 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2 LGUs (Dipaculao, Aurora & Mexico, Pampanga declined Sy 2012-2013 implementation
IV-A | 142 | 3491 | 180572 | 0 | 0 | 168835 | 0 | 413 | 22507 |  | 0 | 12.4643 | 288368400 | 273270120 | 62884272.54 | 94.7642 | 94.7642 | 8 | 141 | 102 |  | procurement of food commodities still on process in some LGUs; upland communities road not yet accessible for the delivery of food commodities | 4 | 4 | 15 | 4 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
IV-B | 72 | 2860 | 113095 | 0 | 2114 | 67046 | 0 | 1505 | 44546 |  | 0 | 39.3881 | 179100200 | 110380835 | 15915065 | 61.6308 | 61.6308 | 4 | 72 | 72 |  | partial delivery of utensils done | 5 | 5 | 16 | 5 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
V | 114 | 4583 | 142480 |  | 0 | 0 | 0 | 3756 | 122382 |  | 0 | 85.8942 | 235663800 | 190915920 | 0 | 81.012 | 81.012 | 2 | 93 | 93 |  | 3 LGUs to start this week while 3 LGUs with previous unliquidated funds (past projects) | 6 | 6 | 12 | 6 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 30 LGUs will not implement SY 2012-2013 feeding
VI | 133 | 5557 | 198360 |  | 5445 | 193348 | 133 | 5337 | 188568 |  | 0 | 95.0635 | 313429000 | 301291200 | 51326712 | 96.1274 | 96.1274 | 1 | 133 | 133 | 133 | procurement of food commodities still on process in some LGUs; upland communities road not yet accessible for the delivery of food commodities | 7 | 7 | 5 | 7 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
VII | 132 | 4173 | 147403 | 0 | 4592 | 153996 | 0 | 1281 | 37346 |  | 0 | 25.336 | 233334600 | 182366400 | 40835700 | 78.1566 | 78.1566 | 6 | 132 | 132 |  | partial delivery of utensils done | 8 | 8 | 1 | 8 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
VIII | 143 | 3940 | 113768 | - | 0 | 0 | 0 | 226 | 6215 |  | 0 | 5.4629 | 130107600 | 20377500 | 0 | 15.662 | 15.662 | 9 | 133 | 133 | 133 | 4 LGUs to start this week while 3 LGUs with previous unliquidated funds (past projects) | 9 | 9 | 2 | 9 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
IX | 72 | 2228 | 110000 | 0 | 2226 | 110391 | 0 | 2226 | 107535 | 23383862.5 | 0 | 97.7591 | 176971800 | 169540800 | 0 | 95.801 | 95.801 | 1 | 72 | 72 |  | procurement of food commodities still on process in some LGUs; upland communities road not yet accessible for the delivery of food commodities | 10 | 10 | 13 | 10 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
X | 93 | 3110 | 115430 | - | 3052 | 115430 |  | 3137 | 115430 |  | 0 | 100 | 181748800 | 180070800 | 0 | 99.0767 | 99.0767 | 1 | 92 | 92 |  | partial delivery of utensils done | 11 | 11 | 9 | 11 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
XI | 49 | 2515 | 89191 | 0 | 3054 | 118966 | 0 | 1764 | 92574 |  | 0 | 103.793 | 144626800 | 111088800 | 0 | 76.8107 | 76.8107 | 3 | 49 | 49 | 46 | 5 LGUs to start this week while 3 LGUs with previous unliquidated funds (past projects) | 12 | 12 | 11 | 12 | 10131 | 7704 | 76.0438 | 1773 | 17.5007 | 31 | 0.30599 | 8654 | 85.421 | 814 | 8.0347 | 64 | 0.63172 | 12.3313 | -54.0891 | 106.4516
XII | 50 | 2757 | 93440 | - | 3010 | 93440 | 0 | 1959 | 64857 |  | 0 | 69.4103 | 149407400 | 141483480 | 0 | 94.6964 | 94.6964 | 1 | 50 | 50 | 50 | procurement of food commodities still on process in some LGUs; upland communities road not yet accessible for the delivery of food commodities | 13 | 13 | 10 | 13 | 93567 | 71038 | 75.9221 | 19913 | 21.2821 |  | 0 | 78973 | 84.4026 | 11720 | 12.5258 |  | 0 | 11.1701 | -41.144 | #DIV/0! |  | Cotabato City - Maguindanao
NCR | 17 | 1920 | 161528 | - | 2030 | 152228 | 0 | 1742 | 139816 |  | 0 | 86.5584 | 186830600 | 137640534 | 0 | 73.6713 | 73.6713 | 7 | 17 | 17 | 17 | partial delivery of utensils done | 14 | 14 | 7 | 14 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
CAR | 77 | 2020 | 84982 | - | 2086 | 43662 | 0 | 1950 | 45100 |  | 0 | 53.0701 | 72246600 | 59108400 | 0 | 81.8148 | 81.8148 | 1 | 77 | 67 | 1 | 6 LGUs to start this week while 3 LGUs with previous unliquidated funds (past projects) | 15 | 15 | 14 | 15 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
CARAGA | 73 | 1920 | 67990 | 0 | 2048 | 67990 | 0 | 1946 | 63493 |  | 0 | 93.3858 | 110453800 | 106064400 | 0 | 96.026 | 96.026 | 1 | 71 | 69 |  | procurement of food commodities still on process in some LGUs; upland communities road not yet accessible for the delivery of food commodities | 16 | 16 | 8 | 16 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
ARMM | 115 | 1340 | 70154 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 84891510 | 0 | 10461900 | 0 | 0 | 5 | 42 | 42 |  | partial delivery of utensils done | 17 | 17 | 12 | 17 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Ongoing downloading of 2nd tranche to MSWDOs
NPMO
TOTAL | 1630 | 52314 | 2006549 | 0 | 32955 | 1382585 | 133 | 35212 | 1312725 | 58118112.5 | 0 | 65.422 | 3121416510 | 2456104272 | #REF! | 78.6856 | #REF! |  | #REF! | #REF! | #REF! | [7 empty] | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | 3121416510
Prepared by: |  |  | Reviewed by: | [8 empty] | Approved by: |  | Approved by: | [29 empty] | 188083890 | NPMO
_________________ |  |  | ___________________________ | [8 empty] | _____________________________ |  | _____________________________________ | [29 empty] | 3309500400
VICKY B. ESPIÑA |  |  | IRISH M. OPEÑA | [8 empty] | JESUSA A. CABILAO |  | MARGARITA V. SAMPANG, CESO III
Statistician II |  |  | SWO IV | [8 empty] | SWO V - Division Chief |  | Director, PSB